SCAFFOLD HEALTH

Project Timeline & Roadmap

Prepared: July 25, 2026     Status: Weeks 1–3 complete · Week 4 in progress

Week dates are approximate, back-calculated from the project start date, and may be adjusted.

# Overview

Scaffold Health is a clinical knowledge platform for physical therapy and orthopedic rehab clinics, built on an event-sourced CQRS architecture. It structures scattered clinical documents and patient check-ins into an auditable Patient Knowledge Profile, powering a Therapist Copilot and a Patient Assistant. The MVP clinical wedge is ACL reconstruction rehab.

This is a five-week build. The first three weeks (planning, foundational skeleton, and core platform) are complete. The remaining two weeks add the Timeline, retrieval-augmented Copilot briefs, the Patient Assistant, and an agentic evolution of the Therapist Copilot.

## Week 1 — Project Planning   (Jul 4–10)

● COMPLETE

- Product scope defined — Patient Knowledge Profile, Therapist Copilot, Patient Assistant, ACL-reconstruction MVP wedge

- PRD authored — problem statement, target users, in/out of scope, Definition of Done

- Core architecture designed — event-sourced CQRS, append-only event log, Knowledge Builder, Timeline/RAG projector

- Build plan — milestone breakdown (M1–M9) sequenced

## Week 2 — Supporting Docs & Project Skeleton   (Jul 11–17)

● COMPLETE

- Repository initialized — README, .gitignore, PRD committed

- Project skeleton — Docker Compose stack, FastAPI app, package layout scaffolded

- M1 — Event store — append-only event store with DB-level enforcement, plus full test suite

- M2 — Therapist authentication — signup (registration-code gated), login, token refresh

## Week 3 — Core Platform Build   (Jul 18–24)

● COMPLETE

- M3 — Patients — intake, invite-link creation, role-split query API (therapist vs. patient views)

- M4 — Documents — PDF upload with async OCR/LLM text extraction and status tracking

- M5 — Check-ins & phases — pain level + note submission, therapist-only forward-only phase progression

- M6 — React frontend — auth flows, therapist caseload dashboard, patient portal

- M7 — LLM fact extraction — Gemini-backed, per-field provenance, merge logic, contradiction detection, needs-review flagging; Knowledge Builder; golden evaluation set (12 notes, precision/recall/F1)

At this point, 10 of the 12 MVP Definition-of-Done items are complete: therapist signup/login, patient creation + invite, patient activation, document extraction with provenance, contradiction badges, forward-only phase advancement, patient check-ins, full event replay, the golden evaluation run, and docker compose up for the whole stack.

## Week 4 — Timeline, RAG & AI-Assisted Interfaces   (Jul 25–31)

● UPCOMING

Covers the two remaining Definition-of-Done items — Prep Briefs and the Patient Assistant — plus a new Patient Timeline feature.

- Patient Timeline — a Timeline projector/read-model surfacing curated clinical milestones — phase advances, extracted milestone facts, and document-extraction completions — in chronological order per patient, shown on both the therapist dashboard and the patient portal

- RAG indexing pipeline — chunk and embed residual unstructured text (document narrative, free-text notes, guideline corpus) into a per-patient RAG index; a schema-allowlist check rejects any chunk that near-matches a known structured field

- M8 — Prep Briefs — endpoint assembling Knowledge Profile + Timeline events since the last brief + relevant RAG context into three sections (Since last visit / Flags / Suggested focus), wired into the therapist dashboard

- M9 — Patient Assistant — scoped single-turn Q&A against a patient-education-only RAG corpus, with symptom/urgent-sounding questions redirected to the clinic instead of answered, wired into the patient portal

## Week 5 — Agentic Therapist Copilot & Wrap-up   (Aug 1–7)

● UPCOMING

The MVP Copilot is a single structured LLM prompt with no agent orchestration. Week 5 deliberately extends past that MVP design into agentic tool-use, building on the Week 4 Prep Brief.

- Multi-step case review — the agent iteratively queries the Knowledge Profile, Timeline, and RAG context itself while drafting the brief, rather than working from one pre-assembled prompt

- Follow-up Q&A on a brief — the therapist can ask a clarifying question about a generated brief, and the agent re-queries the relevant data to answer

- Stretch goals — caseload-wide triage (proactively surfacing patients needing review) and dedicated trend/adherence tools, time-permitting

- Guardrail — advisory-only — the agent never writes to a patient’s care plan or profile directly

- DoD verification — end-to-end verification against all 12 Definition-of-Done items

- Evaluation pass — testing and evaluation pass covering RAG, brief, assistant, and agentic-copilot quality

- Wrap-up — documentation cleanup and final demo preparation

# Summary

| Week | Dates | Focus | Status |
| --- | --- | --- | --- |
| 1 | Jul 4–10 | Project planning, PRD, architecture design | Complete |
| 2 | Jul 11–17 | Supporting docs, project skeleton, event store (M1), auth (M2) | Complete |
| 3 | Jul 18–24 | Patients (M3), documents (M4), check-ins/phases (M5), frontend (M6), extraction (M7) | Complete |
| 4 | Jul 25–31 | Patient Timeline, RAG index, Prep Briefs (M8), Patient Assistant (M9) | Upcoming |
| 5 | Aug 1–7 | Agentic Therapist Copilot (multi-step review, follow-up Q&A), DoD wrap-up | Upcoming |